## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tanvi | 2026-02-27 | Image not displayed after upload | Sprint 1 | Tanvi | User Interface | Fixed image path using flask route | 2026-02-27 | closed | working fine
2 | Tanvi | 2026-02-27 | OCR not extracting Aadhaar correctly | Sprint 1 | Tanvi | Logical | Improved regex pattern | - | closed | Accuracy improved
3 | Tanvi | 2026-02-27 | Gender/DOB detection incorrect | Sprint 1 | Tanvi | Logical | Fixed txt parsing logic | 2026-03-09 | Closed | Verified
4 | Tanvi | 2026-03-09 | Fraud reasons not showing properly | Sprint 2 | Tanvi | User Interface | Fixed Jinja rendering logic | - | closed | Working fine
5 | Tanvi | 2026-03-09 | Model giving wrong fraud predictions | Sprint 2 | Tanvi | Logical | Adjusted prediction threshold | - | open | needs tuning
6 | Tanvi | 2026-03-09 | Duplicate file overwrite issue | Sprint 2 | Tanvi | Maintainability | Added unique filename saving logic | - | open | Tested
7 | Tanvi | 2026-03-23 | OCR text formatting inconsistent | Sprint 3 | Tanvi | Standards | Standard output formatting | 2026-03-23 | open | In progress
8 | Tanvi | 2026-03-23 | Slow response during prediction | Sprint 3 | Tanvi | Logical | Optimizing model execution | - | Open | needs improvement
9 | Tanvi | 2026-03-23 | PDF report generating properly | Sprint 3 | Tanvi | Logical | Debugging report generation logic | - | open | in progress

## Sheet2
Logical
User Interface
Maintainability
Standards
Others